## May 9th COMBINED)
HOTEL | Island/County | Notes from May 7th and 9th | STATUS | Confirmed | Pending | Declined
Ala Moana Hotel by Mantra | Oahu | Spoke with Matt McGuigan, Hotel Manager - they are behind this 100% and have started doing it. | Confirmed | X
Castle Hilo Hawaiian Hotel | Hawaii Island | We spoke to Kendle Kelson Front Desk Manager referred us to Jeff Caminos (Senior VP) at Corp office. Jeff confirmed he reached out to all of his property GMs and they are all currently in compliance with the policy. Additionally, they are stating that they have not recieved notifications from the airport that guests have arrived on island. | Confirmed | X
Castle Kaha Lani Resort | Kauai | Confirmed; Currently doesn't have any quarantine guests | Confirmed | X
Castle Kamaole Sands | Maui | Confirmed with Betty, Front Desk Manager | Confirmed | X
Courtyard Maui Kahului Airport | Maui | Confirmed with Hyrum Kintaro, Front Desk Manager. Original email was resent to Hyrum and GM Marc Walz. | Confirmed | X
Darmic Waikiki Banyan | Oahu | Confirmed - Jamie (Owner/GM) Don't have keys. They use a code. They let people in the room and do not give them the code. Visitors also sign a document produced by Banyan asking for compliance to 14-day quarantine. | Confirmed | X
Embassy Suites by Hilton Oahu Kapolei | Oahu | Confirmed - Reid Yoshida (GM) following policy | Confirmed | X
Embassy Suites by Hilton Waikiki Beach Walk | Oahu | Confirmed - Simeon Miranda (GM) following policy | Confirmed | X
Hawaii Vacation Condos by Outrigger | Hawaii Island | Confirmed; currently have no guests | Confirmed | X
Hilton Garden Inn Kauai Wailua Bay | Kauai | Confirmed; Spoke with Raymond, all guests have respectful | Confirmed | X
Honua Kai Resort & Spa | Maui | Confirmed with Front Desk Manager Kelsey. | Confirmed | X
Hotel Coral Reef | Kauai | Confirmed; currently have no quarantine guests | Confirmed | X
Hotel La Croix | Oahu | Confirmed - Aaron Merdock (Resident Manager) & Ben Rafter are following the policy | Confirmed | X
Hotel Renew | Oahu | Confirmed - Adrian Perez (GM) | Confirmed | X
Hyatt Place Waikiki Beach | Oahu | Confirmed - Ihab Kherati (GM) | Confirmed | X
Hyatt Regency Waikiki Beach Resort & Spa | Oahu | Spoke to HR -she said they are not taking in new guests at this time. If they do, they will make sure they have limited access to a key | Confirmed | X
Kauai Beach Resort | Kauai | Participating - and they have no guests to date. | Confirmed | X
Kiahuna Plantation by Castle Resorts | Kauai | Spoke to GM. They received the letter and confirmed participation with policy. | Confirmed | X
Kilauea Lodge and Restaurant | Hawaii Island | Janet is aware (old school lock and key) they were planning on walking guests to the rooms. Their doors are free lock, so they are looking into it. All the guests are kama'aina. no visitors. They all cancelled after the first mandatory was installed. They would reach out to HTA if anyone does check in. All local regulars who are checking in. | Confirmed | X
Koloa Landing Resort at Poipu, a Marriott Autograph Collection Resort | Kauai | Spoke with andy email received and only hotels for heroes guests are currently at the hotel. Confirmed participation. | Confirmed | X
Marriott's Kauai Beach Club | Kauai | Catherine-housekeeping and front desk manager; the hotel procedure is the guests will be escorted to their rooms and will not be issuing them a key. At this time they do not have any guests. | Confirmed | X
Marriott's Kauai Lagoons - Kalanipuu | Kauai | Candy-front desk agent. No key is given to any guest-currently there are no guests at the hotel | Confirmed | X
Marriott's Ko Olina Beach Club | Oahu | Kyle-FB will make sure that any new guest from the mainland will have limited access to a room key. So far, they only have oahu guests and the current guests have been at the hotel since Dec 2019 | Confirmed | X
Marriott's Maui Ocean Club | Maui | Confirmed with security office that they have put policy into place. Spoke with Amver. | Confirmed | X
Marriott's Maui Ocean Club Napili & Lahaina Villas | Maui | Confirmed with security office that they have put policy into place. Spoke with Amver. | Confirmed | X
Marriott's Waiohai Beach Club | Kauai | Betty- front desk manager: hotel procedure is they are not giving the guests any keys. The guest(s) will be escorted to their rooms and the rooms are monitored by security. They currently have one guest. | Confirmed | X
Molokai Shores | Molokai | They are complying with the policy | Confirmed | X
Napili Kai Beach Resort | Maui | Spoke with Gregg Nelson - They have no guests but will issue single use key cards to any guests that must be quarantined. | Confirmed | X
Outrigger Waikiki Beach Resort | Oahu | Cici-FB have been doing the limited room key access since march2020. they understand the process and procedure. They had one guest that broke the quarantine rule and they called HPD | Confirmed | X
Pagoda Hotel | Oahu | Manager on duty-Paul : they are only giving the guests access to a room key for one day. After that, the guests will not have any access to their key. | Confirmed | X
Park Shore Waikiki | Oahu | Spoke to Front Desk- she said that their procedure is to give guests only one day access to a room key. If the visitor breaks quarantine, they will call HPD. I also gave her HTA's call center number | Confirmed | X
Plantation Hale Suites | Kauai | The GM is on medical leave-forward the email to front desk. their hotel will follow the guidelines. | Confirmed | X
Residence Inn Maui Wailea | Maui | Spoke with Kaleo Kenui, GM. They are not issuing any keys and have not been for three weeks. They let the guest into the room and leave them there. | Confirmed | X
Sheraton Kauai Coconut Beach Resort | Kauai | Chris Machorek - GM confirm participation in program. | Confirmed | X
Sheraton Kona Resort & Spa at Keauhou Bay | Hawaii Island | Confirmed; they haven't been giving guests any keys and has security escort them to their rooms. All guests were compliant. | Confirmed | X
The Cliffs at Princeville | Kauai | Thomas Klein front office manager- no guest so far but will follow the new procedure | Confirmed | X
The Hotel Coral Reef | Kauai | Line was busy, left VM. Spoke to FD Alicia McGurn and they are participating. | Confirmed | X
The Laylow, Autograph Collection | Oahu | I had to forward Robert the email. They currently are not implement this but has no problem complying with it. | Confirmed | X
The Westin Kaanapali Ocean Resort Villas | Maui | Spoke with Front Desk Manager Ohia - They do not have any incoming reservations and have already put this policy into place. | Confirmed | X
The Westin Nanea Ocean Villas | Maui | Spoke with Front Desk Manager Steve Aheog. They have enacted this policy. | Confirmed | X
Wailea Beach Villas, A Destination Luxury Hotel | Maui | Spoke with Christy - Owners Liaison - They have not had any quarantine guests and will issue single use key cards if they do. | Confirmed | X
Royal Sea Cliff | Hawaii Island | Confirmed Participation | Confirmed | X
The ISO | Kauai | Confirmed Participation | Confirmed | X
Courtyard Oahu North Shore | Oahu | Working on implementingnew procedures. Their team is trying to figure it out tehnically. Dave has his AGM workig on it. No IT specialists on hand, but they are trying to figure it out internally. Should have it in place by EOD Monday. They are already reporting people on property who are violating the rules. | Confirmed | X
Castle Waikiki Shore | Oahu | Spoke with Front Desk Ryan Leu, they are confirmed for this policy. Have not had any quarantined guests but have been instructed to issue single use key cards. | Confirmed | X
Maui Beach Hotels (OSL) | Maui | They are setting the policy in place | Confirmed | X
The Imperial Hawaii Resort | Oahu | Spoke to FD Keola Willing and they are participating, no new guest. Telephone number is 923-1827. | Confirmed | X
Banyan Harbor Resort | Kauai | Confirmed. Spoke with Jen, Front Desk Manager. They will be issuing single use room keys. | Confirmed | X
Best Western Pioneer Inn | Maui | Confirmed. Spoke with Marc Guerrera, GM. They are not accepting reservations until quarantine rules are lifted | Confirmed | X
Equus Hotel | Oahu | Confirmed. Renee Kahumoku, Guest Services Manager. | Confirmed | X
Ilikai Hotel & Luxury Suites | Oahu | Confirmed. They are not taking reservations until quarantine policies are lifted. | Confirmed | X
Maui Coast Hotel (10 rooms available for program) | Maui | Confirmed with Joanna Awai (GM)- complying with policy | Confirmed | X
Pacific Marina Inn | Oahu | Confirmed - Policy is implemented. Spoke to Christopher Gagnon (GM) 808-389-3980 | Confirmed | X
Residence Inn by Marriott Oahu - Kapolei | Oahu | Confirmed - Policy is implemented - Spoke to Brian Hunnings 808-777-0211 (GM) | Confirmed | X
SurfJack Hotel & Swim Club | Oahu | Confimred - Policy has been implemented. Lynette Eastmann (GM) | Confirmed | X
The Laylow, Autograph Collection | Oahu | Confirmed-will comply with policy, per Robert Friedl (GM) | Confirmed | X
The Westin Princeville Ocean Resort Villas | Kauai | Confirmed - will enforce policy, per Denise, GM. Worth noting that they're closed until at least 5/31 or when quarantine requirement lifts | Confirmed | X
Trump International Hotel Waikiki | Oahu | Confirmed - will enforce policy with Scott | Confirmed | X
Waimea Plantation Cottages | Kauai | Confirmed - will enforce policy with Jasmine, MOD for 5.9 / GM Gregg Enright is aware, Lori is AGM, Jasmine is Rooms Director | Confirmed | X
Fairway Villas Waikaloa | Hawaii Island | Confirmed - will enforce policy, spoke to GM Kris Nickelsen | Confirmed | X
Ka'anapali Beach Hotel | Maui | Confirmed - will enforce policy, spoke with Mike White / but they have no incoming reservations, and have just one long-stay guest from November in house. | Confirmed | X
Airport Hotel Honolulu | Oahu | Ashley Kanaiaupuni'iua (manager on duty) - Confirmed GM implemented policy and are participating. | Confirmed | X
Kauai Inn | Kauai | Left a message . Called and GM indicated that they are not participating because they have hard keys. | Declined |  |  | X
Maui Kaanapali Villas | Maui | Spoke with Operations Manager Mark. NOT CURRENTLY USING THIS PROTOCOL. | Declined |  |  | X
Royal Grove Waikiki | Oahu | Spoke to the manger on duty-they have four guest in quarantine; they are allowing them to have their key because it is an apartment style hotel. They are monitoring and keeping an eye out for these current guest. Per GM, due to staff shortage they are not able to implement this policy | Declined |  |  | X
Grand Nani Loa Hotel | Hawaii Island | Spoke with Director of Revenue Terry. They are not in agreement with this protocol at this time. They support the overall initiative, however, they are not getting the calls from the airport promptly. In many cases its after the guest has checked in. In some cases it has been a full day after the guest had arrived. They have at least 100 national guard staying in house and even some local residents. They have been doing a good job at enforcing the 14-day quarantine, they have had 3 individuals arrested recently. Their note is that they would be much more open to this idea if the airport can notify them of the incoming guest before they actually arrive. They also stated that local law enforcement needs to be on board, in most cases they will only give a warning and the enforcement falls back on the hotel. The hotel is currently short staffed and cannot be policing everyone that comes in. They would need to know who is under the mandatory quarantine. | Declined |  |  | X
Aston Waikiki Sunset | Oahu | There are no new reservations. All the existing reservations from off island have cancelled in April. They will reopen reservations in June. They are currently only servicing people who have been in house. They are open to installing the one key protocol but they need to have procedures in place. This includes how they handle guests who do not want to comply. It was also brought up that the enforcement needs to be done at the airport. Are the airports notifying the hotels of incoming guests in a timely fashion? | Pending |  | X
Aqua Aloha Surf Waikiki | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aqua Bamboo Waikiki | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aqua Oasis | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aqua Ohia Waikiki | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aqua Palms Waikiki | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aqua Skyline at Island Colony | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Aston at Papakea Resort | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston at the Executive Centre Hotel | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston at the Maui Banyan | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston at the Waikiki Banyan | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston at The Whaler on Kaanapali Beach | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Kaanapali Shores | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Mahana at Kaanapali | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Maui Hill | Maui | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by Monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Paki Maui | Maui | Spoke with front desk manager anna enomoto. She was not familiar with the policy. Forwarded her the original email that was sent out. | Pending |  | X
Aston Waikiki Beach Hotel | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Waikiki Beach Tower | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Aston Waikiki Circle Hotel | Oahu | JP spoke to Grant James (VP). James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels that are closed. | Pending |  | X
Hampton Inn & Suites Oahu at Kapolei | Oahu | JP spoke to Grant James. (VP) James and his executive team are in discussions now. He said they would respond by monday. JP asked for a list of Hotels that can confirm now, hotels that have issues and why, and Hotels ttha are closed. | Pending |  | X
Holiday Inn Express Waikiki Beach | Oahu | STILL PENDING. Spoke with Shauna Shimamoto, Assistant Front Desk Manager. Hotel management is meeting on this issue on Monday. | Pending |  | X
Kamuela Inn | Hawaii Island | Manager wont be back till Monday, they use old school keys (neighbor Island --> essential worker) Mostly Big Island residents and essential workers (hotels for heroes participant) | Pending |  | X
Luana Waikiki Hotel & Suites | Oahu | Confirmed Martha Vasai front desk that they are doing the key restriction by activing the key for one day. She is not sure if the GM knows but they are complying with the policy. | Pending |  | X
Lumeria Maui | Maui | NO ANSWER AT DESK OR ADMIN OFFICE | Pending |  | X
|  |  | Total Responses | Confimred | Pending | Declined
|  |  | 91 | 63 | 24 | 4